## project
Project Plan - Reactive Spaces
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
desktop -> synced peer list | 1 | 6 | 1 | 14 | 50%
websocket -> local kinect data | 1 | 6 | 1 | 14 | 25%
Javascript -> local Kinect data | 1 | 6 | 1 | 14 | 0%
desktop -> remote kinect data | 7 | 7 |  |  | 0%
websocket -> remote kinect data | 7 | 7 |  |  | 0%
Javascript -> remote kinect data | 7 | 7 |  |  | 0%
desktop -> user data | 14 | 7 |  |  | 0%
websocket -> userdata | 14 | 7 |  |  | 0%
Javascript -> user data | 14 | 7 |  |  | 0%
desktop -> game session info | 21 | 7 |  |  | 0%
websocket -> game session info | 21 | 7 |  |  | 0%
Javascript -> game session info | 21 | 7 |  |  | 0%
desktop -> peer game sessions | 28 | 7 |  |  | 0%
desktop -> session / peer matching | 28 | 7 |  |  | 0%
debug and testing feedback | 42 | 9 |  |  | 0%
Create Concept | 1 | 4 |  |  | 100%
Design visuals | 7 | 7 |  |  | 0%
Create Assets | 14 | 7 |  |  | 0%
Dot Generation | 7 | 7 |  |  | 0%
Colecting Dots | 14 | 7 |  |  | 0%
Large Dot Creation | 21 | 7 |  |  | 0%
Large dot functionality | 21 | 7 |  |  | 0%
Colour assignment | 28 | 7 |  |  | 0%
Implement scoring system | 35 | 7 |  |  | 0%
Implement win/lose | 35 | 7 |  |  | 0%
Interface | 35 | 7 |  |  | 0%
Remote Interaction | 35 | 13 |  |  | 0%
Create Poster, info cards | 14 | 7 |  |  | 0%
Contact lower IMD Students | 28 | 12 |  |  | 0%
Website - Concept | 1 | 4 |  |  | 0%
Website - Final | 63 | 8 |  |  | 0%
Video | 63 | 8 |  |  | 0%
Stickers | 14 | 7 |  |  | 0%
Contact BIT school about demo day | 28 | 12 |  |  | 0%
Secure equipment for demo day | 35 | 12 |  |  | 0%
Atrium - public demo | 49 | 10 |  |  | 0%
Find subject(s) to use API | 28 | 12 |  |  | 0%
Create user testing form evaluation | 35 | 12 |  |  | 0%
Support subjects during development | #VALUE! | #VALUE! |  |  | 0%

## Tasks
ID | Section | Task | Assigned | Status | Requires | Date | Days Left | Day End | Day Start
1 | API | desktop -> synced peer list | Ryan | Complete |  | 2014-10-17 | done | 7 | 1
2 | API | websocket -> local kinect data | Ryan | Complete |  | 2014-10-17 | done | 7 | 1
3 | API | Javascript -> local Kinect data | Ryan | Complete |  | 2014-10-17 | done | 7 | 1
4 | API | desktop -> remote kinect data | Ryan | Complete |  | 2014-10-24 | done | 14 | 7
5 | API | websocket -> remote kinect data | Ryan | Complete |  | 2014-10-24 | done | 14 | 7
6 | API | Javascript -> remote kinect data | Ryan | Complete |  | 2014-10-24 | done | 14 | 7
7 | API | desktop -> user data | Ryan | Complete |  | 2014-10-31 | done | 21 | 14
8 | API | websocket -> userdata | Ryan | Complete |  | 2014-10-31 | done | 21 | 14
9 | API | Javascript -> user data | Ryan | Complete |  | 2014-10-31 | done | 21 | 14
10 | API | desktop -> game session info | Ryan | Complete |  | 2014-11-07 | done | 28 | 21
11 | API | websocket -> game session info | Ryan | Complete |  | 2014-11-07 | done | 28 | 21
12 | API | Javascript -> game session info | Ryan | Complete |  | 2014-11-07 | done | 28 | 21
13 | API | desktop -> peer game sessions | Ryan | Complete |  | 2014-11-14 | done | 35 | 28
14 | API | desktop -> session / peer matching | Ryan | Complete |  | 2014-11-14 | done | 35 | 28
15 | API | debug and testing feedback | Ryan | Not Started |  | 2014-11-30 | 25 | 51 | 42
16 | API | Kinect v2 Support | Ryan | Not Started |  | 2014-12-05 | 30 | 56 | 49
17 | Game | Create Concept | Marco, Zara | Complete |  | 2014-10-15 | done | 5 | 1
18 | Game | Design visuals | Marco | In-Progress |  | 2014-10-24 | -12 | 14 | 7
19 | Game | Create Assets | Marco | Not Started |  | 2014-10-31 | -5 | 21 | 14
20 | Game | Dot Generation | Zara | In-Progress |  | 2014-10-24 | -12 | 14 | 7
21 | Game | Colecting Dots | Zara | Not Started |  | 2014-10-31 | -5 | 21 | 14
22 | Game | Large Dot Creation | Zara | Not Started |  | 2014-11-07 | 2 | 28 | 21
23 | Game | Large dot functionality | Zara | Not Started |  | 2014-11-07 | 2 | 28 | 21
24 | Game | Colour assignment | Zara | Not Started |  | 2014-11-14 | 9 | 35 | 28
25 | Game | Implement scoring system | Zara | Not Started |  | 2014-11-21 | 16 | 42 | 35
26 | Game | Implement win/lose | Zara | Not Started |  | 2014-11-21 | 16 | 42 | 35
27 | Game | Interface | Zara | Not Started |  | 2014-11-21 | 16 | 42 | 35
28 | Game | Remote Interaction | Zara | Not Started |  | 2014-11-27 | 22 | 48 | 35
29 | Marketing | Create Poster, info cards | Marco | Not Started |  | 2014-10-31 | -5 | 21 | 14
30 | Marketing | Contact lower IMD Students | Marco | Not Started |  | 2014-11-19 | 14 | 40 | 28
31 | Marketing | Website - Concept | Matt, Marco | Complete |  | 2014-10-15 | done | 5 | 1
32 | Marketing | Website - Initial | Matt | Complete |  | 2014-10-24 | done | 14 | 7
33 | Marketing | Website - Final | Matt | In-Progress |  | 2014-12-20 | 45 | 71 | 63
34 | Marketing | Video | Matt | Not Started |  | 2014-12-20 | 45 | 71 | 63
35 | Marketing | Stickers | Marco | Not Started |  | 2014-10-31 | -5 | 21 | 14
36 | Marketing | Contact BIT school about demo day | Marco | Not Started |  | 2014-11-19 | 14 | 40 | 28
37 | Marketing | Secure equipment for demo day | Marco | Not Started |  | 2014-11-26 | 21 | 47 | 35
38 | Marketing | Atrium - public demo | All | Not Started |  | 2014-12-08 | 33 | 59 | 49
39 | Testing | Find subject(s) to use API | Marco | Not Started |  | 2014-11-19 | 14 | 40 | 28
40 | Testing | Create user testing form evaluation | All | Not Started |  | 2014-11-26 | 21 | 47 | 35
41 | Testing | Support subjects during development | Marco | Not Started |  | N/A | #VALUE! | #VALUE! | #VALUE!
Formulas:
Days Left = IF(EXACT( [Status], Pickers!$B5), "done", DAYS( [Date], TODAY() ) )
Day End = DAYS( [Date], DATE(2014, 10, 10))

## Pickers
Status
Not Started
In-Progress
Complete